## Dashboard
Manager Task OS: Dashboard
Start here every day: due soon, overdue, waiting, blockers, and project health.
Metric | Count | Status | Count | Priority | Open
Open Tasks | 5 | Not Started | 1 | P0 Critical | 1
Due Today/Tomorrow | 3 | In Progress | 2 | P1 High | 3
Overdue | 1 | Waiting on Others | 1 | P2 Medium | 1
Waiting on Others | 1 | Blocked | 1 | P3 Low | 0
Blocked | 1 | Scheduled | 0
|  | Done | 1
|  | Canceled | 0
Daily Manager Rhythm
Morning 10 min | Clear new tasks and mark what must move today
Midday 10 min | Review delegated/waiting items and remove blockers
End of day 10 min | Update progress and rewrite vague work into a clear next step
Weekly review | Delete low-value tasks and reset the team Top 3
Rule | Every active task needs owner, status, due date, and next step

## Task Inbox
Manager Task OS: Task Inbox
Capture tasks quickly and manage owner, project, status, due date, blockers, and cadence with dropdowns.
ID | Task | Type | Project | Owner | Priority | Status | Due Date | Effort (h) | Progress | Next Step | Today? | Delegated? | Blocker | Last Updated | Notes | Cadence
T-001 | Confirm this week's team Top 3 priorities | Team | Team Management | Me | P0 Critical | In Progress | 2026-06-01 | 1 | 50% | Confirm owner in 15-min standup | Yes | No |  | 2026-06-01 | Update every morning | Weekly
T-002 | Follow up on customer delivery risk list | Project | Customer Delivery | Alice | P1 High | Waiting on Others | 2026-06-02 | 2 | 35% | Waiting for risk rating from Alice | Yes | Yes |  | 2026-06-01 | Need feedback by 3 PM | One-time
T-003 | Approve Q3 budget draft | Decision | Budget Planning | Me | P1 High | Not Started | 2026-06-05 | 1.5 | 0% | Review Finance version | No | No |  | 2026-06-01 |  | Quarterly
T-004 | Compile hiring interview feedback | Meeting | Hiring | HR | P2 Medium | Blocked | 2026-05-30 | 1 | 20% | Ask HR for missing scorecard | Yes | Yes | Missing interviewer scorecard | 2026-06-01 | Overdue example | One-time
T-005 | Archive product improvement meeting notes | Follow-up | Product Improvements | Ben | P2 Medium | Done | 2026-05-31 | 0.5 | 100% | Archive notes | No | Yes |  | 2026-06-01 |  | Weekly
T-006 | Map cross-functional SLA workflow | Project | Process Optimization | Product | P1 High | In Progress | 2026-06-07 | 3 | 65% | Add Legal review node | No | Yes |  | 2026-06-01 |  | Monthly

## Daily Plan
Daily Plan
Use filters in Task Inbox to copy today's tasks here; fixed fields use dropdowns.
ID | Task | Type | Project | Owner | Priority | Status | Due Date | Effort (h) | Progress | Next Step | Today? | Delegated? | Blocker | Last Updated | Notes | Cadence | Today Top 3 | Owner | Next Step
T-001 | Confirm this week's team Top 3 priorities | Team | Team Management | Me | P0 Critical | In Progress | 2026-06-01 | 1 | 50% | Confirm owner in 15-min standup | Yes | No |  | 2026-06-01 | Update every morning | Weekly
T-002 | Follow up on customer delivery risk list | Project | Customer Delivery | Alice | P1 High | Waiting on Others | 2026-06-02 | 2 | 35% | Waiting for risk rating from Alice | Yes | Yes |  | 2026-06-01 | Need feedback by 3 PM | One-time
T-004 | Compile hiring interview feedback | Meeting | Hiring | HR | P2 Medium | Blocked | 2026-05-30 | 1 | 20% | Ask HR for missing scorecard | Yes | Yes | Missing interviewer scorecard | 2026-06-01 | Overdue example | One-time

## Projects
Projects
Track project-level status, owner, next milestone, due date, and formula-driven task progress.
Project | Goal / Notes | Project Owner | Status | Next Milestone | Milestone Date | Total Tasks | Open | Overdue | Completion
Weekly Ops | Run a consistent weekly operating rhythm | Me | In Progress | Confirm agenda | 2026-06-03 | 0 | 0 | 0 | 0%
Customer Delivery | Deliver on time and reduce escalation risk | Alice | Waiting on Others | Close risk list | 2026-06-06 | 1 | 1 | 0 | 0%
Product Improvements | Prioritize product asks and drive roadmap input | Ben | In Progress | Finish demand ranking | 2026-06-10 | 1 | 0 | 0 | 100%
Team Management | Keep team priorities and feedback clear | Me | In Progress | Schedule 1:1s | 2026-06-04 | 1 | 1 | 0 | 0%
Hiring | Move key candidates through interviews | HR | Blocked | Collect scorecards | 2026-06-02 | 1 | 1 | 1 | 0%
Budget Planning | Complete Q3 budget approval | Finance | Not Started | Approve draft | 2026-06-08 | 1 | 1 | 0 | 0%
Process Optimization | Make cross-functional SLA visible | Product | In Progress | Confirm Legal node | 2026-06-14 | 1 | 1 | 0 | 0%
Personal Management | Clear and review personal tasks | Me | Scheduled | Friday review | 2026-06-05 | 0 | 0 | 0 | 0%
Cross-functional | Reduce repeated alignment loops | Me | Not Started | Define handoff checklist | 2026-06-12 | 0 | 0 | 0 | 0%
Risk Handling | Detect and escalate risks quickly | Me | Scheduled | Confirm risk template | 2026-06-09 | 0 | 0 | 0 | 0%
Formulas:
Overdue = COUNTIFS('Task Inbox'!$D6:D205,[Project],'Task Inbox'!$G6:G205,"<>Done",'Task Inbox'!$H6:H205,"<"&TODAY(),'Task Inbox'!$B6:B205,"<>")

## Delegated Waiting
Delegated / Waiting
Use this sheet for delegated, blocked, and waiting-on-others items; fixed fields use dropdowns.
ID | Task | Type | Project | Owner | Priority | Status | Due Date | Effort (h) | Progress | Next Step | Today? | Delegated? | Blocker | Last Updated | Notes | Cadence
T-002 | Follow up on customer delivery risk list | Project | Customer Delivery | Alice | P1 High | Waiting on Others | 2026-06-02 | 2 | 35% | Waiting for risk rating from Alice | Yes | Yes |  | 2026-06-01 | Need feedback by 3 PM | One-time
T-004 | Compile hiring interview feedback | Meeting | Hiring | HR | P2 Medium | Blocked | 2026-05-30 | 1 | 20% | Ask HR for missing scorecard | Yes | Yes | Missing interviewer scorecard | 2026-06-01 | Overdue example | One-time
T-006 | Map cross-functional SLA workflow | Project | Process Optimization | Product | P1 High | In Progress | 2026-06-07 | 3 | 65% | Add Legal review node | No | Yes |  | 2026-06-01 |  | Monthly

## Settings
Settings
Maintain fixed values here. Dropdowns in the workbook reference these lists.
Status | Priority | Task Type | Cadence | Project | Owner
Not Started | P0 Critical | Personal | One-time | Weekly Ops | Me
In Progress | P1 High | Team | Daily | Customer Delivery | Alice
Waiting on Others | P2 Medium | Project | Weekly | Product Improvements | Ben
Blocked | P3 Low | Meeting | Monthly | Team Management | Carla
Scheduled |  | Decision | Quarterly | Hiring | David
Done |  | Follow-up |  | Budget Planning | Finance
Canceled |  | Admin |  | Process Optimization | Product
|  | Risk |  | Personal Management | HR
|  |  |  | Cross-functional | Sales
|  |  |  | Risk Handling | Legal